## KDM-7684
| Component Details | Change description | Responsible | JIRA Ticket Number
| Lock Details Hub | Adding FulfilledOn,AVMRunDate,AgencyCaseAssignmentDate,CumulativeExtensionDays,OriginalCreatorFlag,TexasA6Ind,AppraisalWaiverInd,CustomMiniMI,AVMFSD,HELOCActualBalance,HELOCCreditLimit,SingleClose_OTCInd,VARenovationInd,Recommendation to the Lock Details Hub table | Developer | https://pennymac.atlassian.net/browse/KDM-7676 https://pennymac.atlassian.net/browse/KDM-7736 https://pennymac.atlassian.net/browse/KDM-7597
Sl# | Task | Instructions | Respsonsible | Notes
PREDEPLOYMENT
1 | Have all the naming standards been followed for all assets to be deployed? | Yes | Developer
2 | Check all the assets pointing to the right Project folder (Have you verified "Export" option and check all the respective paths?) | Yes | Developer
3 | Has the view been verified for any errors or dependencies? | Yes | Developer
4 | Are all the required mappings linked/refreshed correctly to the task/taskflow/process/linear task flow? | Yes | Developer
5 | Are there any new parameter files/scripts needing to be commited to gitlab? | No
5a | If yes, has this been commited to gitlab? | No Applicable | Developer
6 | Has the code been reviewed? | Yes | Developer
6a | Have the results of Unit Testing been validated against JIRA requirements? | Yes | Developer
7 | Have the complete unit testing results (screenshot) been uploaed to JIRA? | Yes | Developer
8 | Hub Outage? | No | Jacob Leyba
9 | Full refresh needed? | No | Jacob Leyba
10 | Does this change impact on-prem hub (datatype changes etc. verified with Jacob Leyba)? | Yes | Jacob Leyba
11 | Database Backup steps | None | DBA
12 | Informatica Backup steps | None | DBA
DEPLOYMENT
| SQL - Server - w12-clgsql-1 (Disable Job: MFD LOS PCG Main Control) | Disable Job: MFD LOS PCG Main Control
1 | SQL - Server - w12-clgsql-1 | In order (from zip file "(1 of 2) w12-clgsql-1 (Column Adds)"): 1. (1 of 3) sp_LOS_PCG_LockDetails Alter Stored Proc 20200914 2. (2 of 3) sp_LOS_PCG_LockDetails add columns 20200914 3. (3 of 3 ) sp_LOS_PCG_LockDetails add columns 20200914 | DBA
| EXECUTE FULL REFRESH on w12-clgsql-1 | In order (from zip file "(2 of 2) FULL REFRESH"): 1. FULL REFRESH [PCG_Process].[dbo].[sp_LOS_PCG_LockDetails] 20200914
| SQL - Server - w12-clgsql-1 (Re-Enable Job: MFD LOS PCG Main Control) | Re-Enable Job: MFD LOS PCG Main Control
DEPLOYMENT - FULL REFRESH
| Full refresh |  | DBA
| Full refresh - time |  | DBA
| Run and Schedule the Job (Schedule - run every 15 min) |  | DBA
| Run and Schedule the Job (Schedule - run every 15 min) |  | DBA
| Job Run - time |  | DBA
POST-DEPLOYMENT
1 | Post prod - Developer validation | Post prod - Developer validation | Jacob Leyba
2 | Business validation | Business validation | Fatima/Akshay/Frank
ROLLBACK STEPS
1 | Rollback SQL (Provided in Zip File Folder "ROLLBACKS") | ROLLBACK ORDER AS FOLLOWS ( sproc alter script -> DDL Scripts ) 1.ROLLBACK (1 of 3) sp_LOS_PCG_LockDetails Alter Stored Proc 20200914 2.ROLLBACK (2 of 3) sp_LOS_PCG_LockDetails add columns 20200914 3.ROLLBACK (3 of 3 ) sp_LOS_PCG_LockDetails add columns 20200914 | DBA/Jacob Leyba
| Validation | IT/Business validation